## Table 2022
Site | PLANNING APPLICATION REFERENCE | Date of Permission | Capacity (Gross) | units lost | Site Address | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Status (key at bottom of table) | Capacity at April 2022 | PDL/G | Notes pre-20 | 20 - 21 Notes | 21 - 22 notes
[9 empty] | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
COMPLETIONS AND EXISTING COMMITMENTS (AT APRIL 2020)
Small sites(< 6 Units) with PP | [5 empty] | 162 | 171 | 76
Broxted: Whitehall Hotel, Church End | UTT/16/3549/FUL UTT/19/1932/FUL | 2017-04-24 | 12 |  | Whitehall Hotel, Church End, Broxted, CM6 2BZ | 2 | 4 | [19 empty] | Built | 0 | PDL |  | Completions for 2018/19 amended from 8 to 6 in year 2020/2021
Clavering: Land West Of Stortford Road | UTT/18/3326/PIP UTT/19/2852/FUL | 11/07/2019 24 July 2020 | 8 |  | Land West Of Stortford Road Clavering Essex |  |  |  | 2022/23 Yr1: 8 |  |  |  | 1 | 8 | G |  | Agent 29.10.20 Site currently on the market and under offer to a developer. Anticipate delivery in 2021/22. | UBR/21/0166/DWE (8 new bungalows) work ongoing as of 6.4.22.
Clavering: Land West of Stortford Road | UTT/20/2639/OP | 2021-12-21 | 31 | 1 | Land to the west of Stortford Road, Clavering, Essex |  |  |  | 2022/23 Yr1: -1; 2023/24 Yr2: 6; 2024/25 Yr3: 25 |  |  |  | 3 | 30 | G |  |  | 6.6.22: UTT/22/1103/DFO pending determination. UTT/22/0399/FUL (demolition of dwelling & construction of access road) approved 9.5.22. Aug 22: Agent advised anticipated start on site by the end of the year, then 12 months to first occupation (early 2024) followed by two dwellings per month to completion (mid 2025).
Elsenham: Elsenham Nurseries, Stansted Road | UTT/14/2991/OP UTT/17/0335/DFO UTT/18/0024/FUL | 02-Dec-15 06-Jul-17 12-Mar-18 | 42 | 2 | Elsenham Nurseries Stansted Road, Elsenham CM22 6LJ | 9 | [20 empty] | Built | 0 | G
Elsenham: Land northwest of Henham Road | UTT/17/3573/OP UTT/21/2799/DFO | 2021-12-17 | 350 |  | Land To The North West Of Henham Road Elsenham Hertfordshire |  |  |  | 2022/23 Yr1: 25; 2023/24 Yr2: 50; 2024/25 Yr3: 50; 2025/26 Yr4: 50; 2026/27 Yr5: 50; 2027/28 6: 50; 2028/29 7: 50; 2029/30 8: 25 |  |  |  | 3 | 350 | G |  |  | UTT/21/2799/DFO relates to access road. July 2022 site visit: Works ongoing to access road. 10.6.22: UTT/21/3269/DFO (additional matters) approved 1.6.22. DoCs approved 25.3.22 - 10.5.22. Other DoCs and S73s pending determination. UBR/22/0162/DWEIN (350 dwellings) IN accepted 25.2.22. Aug 22: Agent estimates 25 completions during 22/23 and 50 per year thereafter.
Elsenham: Land south of Rush Lane | UTT/19/0437/OP | 2020-09-04 | 40 |  | Land South Of, Rush Lane, Elsenham |  |  |  | 2025/26 Yr4: 20; 2026/27 Yr5: 20 |  |  |  | 3 | 40 | G |  |  | July 2022 site visit: No works yet undertaken. Aug 22: Agent advised they are no longer instructed but forwarded my query to the new agent. Could not advise further. Owing to new agent involvement, delivery at present still expected.
Elsenham: Land west of Isabel Drive | UTT/19/2470/OP | 2020-12-31 | 99 |  | Land To The West Of, Isabel Drive, Elsenham |  |  |  | 2024/25 Yr3: 49; 2025/26 Yr4: 50 |  |  |  | 3 | 99 | G |  |  | 10.6.22: DoCs approved 31.1.22 - 14.2.22. UTT/21/2461/DFO (submitted 30.7.21) and further DoC pending determination. UBR/22/0462/DWEIN (99 dwellings) submitted 23.5.22 and pending determination.
Felsted: Gransmore Meadow, Chelmsford Road | UTT/17/0034/FUL | 2017-10-10 | 9 |  | Gransmore Meadow Chelmsford Road Felsted | 6 | 3 | [19 empty] | Built | 0 | G
Felsted: Land off Stevens Lane | (UTT/17/0649/OP) UTT/20/0028/DFO | 2018-03-16 | 7 |  | Land Off Stevens Lane Felsted CM6 3NJ |  |  |  | 2022/23 Yr1: 7 |  |  |  | 1 | 7 | G |  |  | July 2022 site visit: ground works underway.
Felsted: Land East And North Of Clifford Smith Drive | (UTT/18/0784/OP) UTT/19/2118/OP | 2019-06-20 | 41 |  | Land East And North Of Clifford Smith Drive Watch House Green Felsted |  |  |  | 2024/25 Yr3: 21; 2025/26 Yr4: 20 |  |  |  | 3 | 41 | G |  | Agent 23.10.20 - increased units to up to 41. Start construction Autumn 2021. First houses delivered Q1 /Q2 2022, maybe at a rate thereafter of 4 dwellings per month. | July 2022 site visit: No works yet undertaken. Aug 22: Agent advised developer hopes to start on-site in mid-'23 with completion in mid-'25.
Felsted: Land To The South Of Braintree Road | UTT/18/3529/OP UTT/21/1755/DFO | 15/01/2020 4-Nov-21 | 30 |  | Land To The South Of Braintree Road Felsted |  |  |  | 2026/27 Yr5: 10; 2027/28 6: 10; 2028/29 7: 10 |  |  |  | 3 | 30 | G |  | UTT/21/1755/DFO approved Nov 2021. UTT/21/1755/DFO approved Nov 2021. Agent 17.12.21 1st completions 2ndQ 2026. Anticipate approx 10 dwellings 2026, 2027 and 2028. Final completions early 2029. | July '22 site visit: No works yet begun.
Felsted: Land West Of Maranello | (UTT/18/1011/OP) UTT/20/0757/DFO | 30/05/2019 23 July 2020 | 28 |  | Land West Of Maranello Watch House Green Felsted |  |  |  | 2022/23 Yr1: 14; 2023/24 Yr2: 14 |  |  |  | 1 | 28 | G |  | Agent 23.10.20 due to commence sometime next month with completion the following year. | July 22 site visit: Works underway - dwellings part-built.
Felsted: Land at Maranello Watch House | (UTT/20/1596/OP) UTT/21/0757/DFO | 2021-02-24 | 7 |  | Land At Maranello Watch House Green Felsted CM6 3EF |  |  |  | 2022/23 Yr1: 7 |  |  |  | 1 | 7 | G |  |  | UBR/21/1003/DWE (seven dwellings) work commenced on all dwellings and ongoing as of 18.5.22.
Felsted: Land West Of Bury Farm | UTT/18/2508/OP | 2021-03-25 | 38 |  | Land West Of Bury Farm Station Road Felsted |  |  |  | 2024/25 Yr3: 15; 2025/26 Yr4: 23 |  |  |  | 4 | 38 | G |  | Agent 4.11.21 start on site likely to be 18-24 months and probably a 2 year build programme | 16.3.22: DFO, DoC, and associated Full pending determination.
Great Chesterford: Land north of Bartholomew Close | (UTT/14/0425/OP) (UTT/17/2745/DFO) UTT/19/2288/FUL | 01-Oct-14 12-Dec17 | 13 |  | Land North Of Bartholomew Close, Great Chesterford CB10 1QA |  |  |  | 2022/23 Yr1: 13 |  |  |  | 1 | 13 | G |  | UDC purchased site. Forecast to complete June 2022 | 2.6.22: UBR/20/0355/DWE (13 dwellings) Work Started 28.4.21 and ongoing as of 21.3.22
Great Dunmow: Kings Head, North Street | UTT/15/1544/FUL | 2015-07-27 | 6 |  | Kings Head North Street Dunmow CM6 1BA | 6 | [20 empty] | Built | 0 | PDL
Great Dunmow: Land East of St Edmunds Lane | (UTT/14/0472/OP) (UTT/17/3623/DFO) UTT/19/1508/FUL | 15-May-15 (11-May-18) | 22 |  | Land east of St Edmunds Lane, Great Dunmow |  |  | 7 | 2022/23 Yr1: 12; 2023/24 Yr2: 3 |  |  |  | 1 | 15 | G |  |  | 10.5.22: BC apps indicate 7 completions 21-22.
Great Dunmow: Land west of Buttleys Lane | UTT/19/2354/OP | 2022-01-19 | 60 |  | Land To The West Of Buttleys Lane Dunmow |  |  |  | 2025/26 Yr4: 30; 2026/27 Yr5: 30 |  |  |  | 4 | 60 | G |  |  | 10.6.22: No further relevant apps. Aug 22: agent confirmed that the site is intended to come forward within the next five-year period. Discussions ongoing re sale of the site to a housebuilder. RM to be submitted post-sale with development commencing post-approval.
Great Dunmow: Land west of Chelmsford Road | UTT/13/1684/OP UTT/17/3106/DFO | 2014-11-04 | 370 |  | Land At Smiths Farm Chelmsford Road Great Dunmow Essex (West of Chelmsford Road) (CM6 1JA??) |  |  |  | 2025/26 Yr4: 30; 2026/27 Yr5: 50; 2027/28 6: 50; 2028/29 7: 50; 2029/30 8: 50; 2030/31 9: 50; 2031/32 10: 50; 2032/33 11: 40 |  |  |  | 1 | 370 | G | UTT/13/1684/OP x 370 app (S106) 23/10/13 ; Phase 1 x 115 detailed, phase 2 all matters reserved except access. | Agent proposes amending details changing 120 dwellings in Yrs1-5 to 0; 250 dwellings in Yrs 6-10 to 180 and 0 dwellings in Yrs 11-15 to 190 (3-Apr-19). Appeal in progress | 4.6.22: UTT/17/3106/DFO pending determination.
Great Dunmow: Land south of Stortford Road, Dunmow | UTT/18/2574/OP | 2022-01-21 | 440 | 1 | Land south of Stortford Road, Dunmow |  |  |  |  | 19 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 20 | [7 empty] | 3 | 439 | G |  |  | Hybrid app: 332 dwellings net as outline; Phase 1 inc 107 dwellings net as full. 6.6.22: UTT/22/1169/PA (DFO query) response provided 26.7.22. Aug 22: Agent estimates RM by June '22, commencement on site in August '23, 20 completions in 23/24, then 50 completions per year thereafter.
Great Dunmow: West of Woodside Way | (UTT/13/2107/OP) (UTT/18/1826/DFO) UTT/20/3419/DFO | 2021-03-29 | 464 |  | Land West Of Woodside Way Woodside Way Great Dunmow |  |  | 44 | 40 | 40 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 25 | [8 empty] | 1 | 420 |  |  |  | July 2022 site visit: 44 dwellings built.
Great Dunmow: West of Woodside Way | (UTT/13/2107/OP) (UTT/18/1826/DFO) UTT/20/2220/DFO | 2021-02-19 | 326 |  | Land West Of Woodside Way Woodside Way Great Dunmow |  |  |  | 2023/24 Yr2: 75; 2024/25 Yr3: 75; 2025/26 Yr4: 75; 2026/27 Yr5: 75; 2027/28 6: 26 |  |  |  | 2 | 326 | G |  | Agent Nov 2021 - commence construction in February 2022. Intend to build an average of 75 dwellings per year 2023-2026
Great Dunmow: Woodlands Park Sectors 1 - 3 | UTT/1006/04/DFO UTT/1809/02/FUL UTT/0395/05/FUL UTT/0496/05/FUL UTT/0386/05/DFO UTT/0392/05/DFO; UTT/0246/07/FUL; UTT/17/1652/FUL | ranges between 26 November 1992 - February 2018 | 1633 |  | Woodlands Park, Great Dunmow | 64 | 8 | 21 | 41 | 40 | 60 | 60 | 50 | 50 | 50 | 50 | 50 | [9 empty] | 1 | 451 | G |  |  | July 2022 site visit: works ongoing. Projections adjusted proportionate to past delivery.
Great Dunmow: Woodlands Park Sector 4 | UTT/2507/11/OP. UTT/13/1663/DFO | 2 August 2012; 31 October 2013 | 125 | 1 | Woodlands Park, Great Dunmow | 0 | 10 | 16 | 2022/23 Yr1: 30; 2023/24 Yr2: 32; 2024/25 Yr3: 35 |  |  |  | 1 | 97 | G | UTT/2507/11/OP. UTT/13/1663/DFO expires 31/10/15. DOC nov/dec 2013. Access work started @ August 2014 |  | July 2022 site visit: both permissions underway. Projections adjusted proportionate to past delivery.
Great Dunmow: Spire House, White Street | UTT/18/0362/FUL | 2018-05-30 | 6 |  | Spire House White Street Great Dunmow CM6 1BD | 6 | [20 empty] | Built | 0 | PDL
Great Dunmow: The Old Mill, Haslers Lane | (UTT/18/3172/PAP3O) UTT/20/2380/PAO3 UTT/20/2376/FUL | 2019-01-14 | 12 |  | The Old Mill Haslers Lane Dunmow CM6 1XS |  |  |  | 2024/25 Yr3: 12 |  |  |  | 2 | 12 | PDL |  | Conversion planned to take place between April 2021 and March 2022. Not starterd Sept 2021 | July 2022 site visit: No works undertaken but building materials on-site. Alternative scheme UTT/22/2161/FUL pending determination.
Great Dunmow: Oaklands, Ongar Road | UTT/17/2238/FUL | 2018-10-05 | 25 |  | Oaklands, Ongar Road, Dunmow, CM6 1EX | 7 | 18 | [19 empty] | Built | 0 | G
Great Dunmow: 14 Stortford Road | UTT/12/5270/FUL | 2012-09-19 | 12 |  | 14 Stortford Road, Great Dunmow, CM6 1DA | 12 | [20 empty] | Built | 0 | PDL
Great Dunmow: Tiggers | UTT/18/3089/FUL UTT/20/3395/FUL | 2019-08-20 | 10 | 1 | Tiggers, Ongar Road Great Dunmow, CM6 1EX |  |  | 3 | 2022/23 Yr1: 6 |  |  |  | 1 | 6 | G |  | Potential loss of 1 mobile home 6.6.22: mobile home removed and 4 dwellings built. | UBR/19/1064/DWE: 3 built 21-22
Great Dunmow: Land adjacent The Granary | (UTT/18/0816/FUL) UTT/20/0121/FUL | 2020-02-06 | 6 |  | Land Adjacent The Granary Stortford Road, Dunmow |  |  |  | 2023/24 Yr2: 6 |  |  |  | 2 | 6 | G |  |  | UTT/22/1727/FUL (amended scheme) approved 2.8.22.
Great Easton: Land between Brocks Mead and the Endway | (UTT/17/0259/OP) UTT/18/0103/DFO | 04-Aug-17 11-May-18 | 9 |  | Land Between Brocks Mead And The Endway Great Easton |  | 1 | 6 | 2022/23 Yr1: 2 |  |  |  | 1 | 2 | PDL |  |  | 4.6.22: 6 built 21-22. Remaining two built 22-23.
Great Hallingbury: Land east of Tilekiln Green | UTT/20/1098/FUL | 2021-11-01 | 15 |  | Land To The East Of Tilekiln Green Great Hallingbury |  |  |  | 2024/25 Yr3: 15 |  |  |  | 2 | 15 | G |  |  | July 2022 site visit: No works undertaken. UBR/22/0600/DWE conditional approval 15.8.22.
Great Hallingbury: Land South East of Great Hallingbury Manor | (UTT/16/3669/OP) UTT/20/0336/DFO | 2019-01-22 | 35 |  | Land South East Of Great Hallingbury Manor, Bedlars Green Road, Tilekiln Green, Great Hallingbury |  |  | 5 | 2022/23 Yr1: 17; 2023/24 Yr2: 13 |  |  |  | 1 | 30 | G |  | Agent 30.10.20 no finalised programme, but given progress re Reserved Matters being granted and outline conditions discharged, trajectory is realistic. | UBR/21/0402/DWE as of 20.4.22: 17 x under construction, 13 x not started, 5 x completed.
Great Hallingbury: Barnmead, Start Hill | UTT/18/1982/FUL UTT/21/2337/FUL | 2019-01-04 | 9 | 1 | Barnmead Start Hill Stane Street Great Hallingbury |  |  |  | 2022/23 Yr1: 8 |  |  |  | 1 | 8 | PDL |  |  | July 2022 site visit: Works commenced.
Great Hallingbury: Marstons, Start Hill | UTT/21/0692/FUL | 2021-05-13 | 8 | 1 | Marstons, Start Hill, Stane Street, Great Hallingbury, Bishops Stortford, Hertfordshire, CM22 7TA |  |  |  | 2022/23 Yr1: -1; 2023/24 Yr2: 8 |  |  |  | 2 | 7 | PDL |  |  | July 2022 site visit: No works undertaken. Original dwelling still in-situ. No further relevant apps. Aug 22: agent advised works are due to commence in October 22.
Great Hallingbury: Newlands, Woodside Cottage & Oakside | UTT/0831/10/FUL | 2010-07-09 | 6 | 3 | Newlands, Woodside Cottage & Oakside, Church Road, Great Hallingbury | 3 | 0 | [19 empty] | 1 | 1 | PDL |  | Applicant 17.11.2020 Two dwellings demolished and 1 semi detached properties and 3 detached built. One dwelling remains but still has consent. One new net detached house. | July 2022: works not yet commenced on final dwelling. Projected completion adjusted accordingly. | bar: 2023/24 Yr2
Hatfield Broad Oak: Great Chalks | UTT/18/0386/FUL | 2019-05-28 | 8 |  | Great Chalks, High Street Hatfield Broad Oak, CM22 7HQ | 4 | 4 | [19 empty] | Built | 0 | PDL
Henham: Land at Old Mead Road | UTT/19/2692/OP | 2021-04-23 | 6 |  | Land at Old Mead Road, Henham |  |  |  | 2026/27 Yr5: 6 |  |  |  | 3 | 6 | PDL |  |  | 6.6.22: UTT/21/1666/OP (amended scheme) allowed on appeal 4.7.22. July 2022 site visit: No works yet undertaken. Aug 22: Agent advised that the site is currently being sold but was not able to advise further. Projection adjusted accordingly.
Henham: Land south of The Farmhouse | UTT/18/3370/OP UTT/21/0009/DFO | 2019-04-15 | 9 |  | Land South Of The Farmhouse, Old Mead Road, Henham |  |  |  | 2022/23 Yr1: 9 |  |  |  | 2 | 9 | PDL |  | Agent 26.10.20 unable to confirm timimg. Reserved matters need to be confirmed by UDC. Doubt it will start before 2022 | UBR/21/0992/DWE (three dwellings) work ongoing as of 17.1.22.
Henham: Land south of Vernons Close | UTT/20/0604/OP | 2021-11-30 | 45 |  | Land South Of Vernons Close Mill Road Henham Hertfordshire |  |  |  | 2023/24 Yr2: 10; 2024/25 Yr3: 35 |  |  |  | 3 | 45 | G |  |  | 10.6.22: No further relevant apps. Aug 22: Agent no longer directly involved but advised the site is very close to being sold to a developer. Estimated 1 year delay for RM consent and pre-commencement, a start by late 2023, first occupation by early 2024, and completion by early 2025.
Little Chesterford: Land To The South West Of London Road | UTT/19/0573/OP UTT/20/3329/DFO | 2020-06-07 | 76 |  | Land To The South West Of London Road, Little Chesterford |  |  |  | 2022/23 Yr1: 16; 2023/24 Yr2: 30; 2024/25 Yr3: 30 |  |  |  | 1 | 76 | G |  | Agent 15.11.21: Pending decision on UTT/20/3329/DFO. If granted, aim to start construction Feb 2022. Build rate 1 per week from Dec 2022 to completion in Feb 2024. | UBR/22/0053/DWE (76 dwellings) work started 21.3.22.
Little Dunmow: Priory Lodge, Station Road | UTT/17/3556/OP UTT/20/2148/DFO | 2018-04-16 | 8 |  | Priory Lodge Station Road Little Dunmow, CM6 3HF |  |  |  | 2022/23 Yr1: 8 |  |  |  | 1 | 8 | PDL |  | Agent 26.1.20 Applicant is keen to build as soon as possible. Early 2023 is a reasonable timeframe for completion but could easily be differ either way. | July 2022 site visit: Works underway.
Little Dunmow: Land at Pound Hill | UTT/19/1789/FUL | 2021-05-21 | 11 |  | Land at Pound Hill, Little Dunmow |  |  |  | 2023/24 Yr2: 11 |  |  |  | 2 | 11 | G |  |  | 7.6.22: DoCs approved 11.1.22 - 13.1.22. UBR/22/0489/DWEIN (14 dwellings) IN accepted 31.5.22.
Little Dunmow: Land East of Station Road | UTT/18/1039/OP UTT/21/3182/FUL | 2019-03-21 | 9 |  | Land To The East Of Station Road, Little Dunmow |  |  |  | 2023/24 Yr2: 9 |  |  |  | 3 | 9 | G |  | Agent 26.10.20 site is up for sale. Unable to confirm timimg. Reserved matters need to be confirmed by UDC. Doubt start before 2022. UTT/21/3182/FUL pending consideration. | 4.6.22: UTT/21/3182/FUL approved 22.4.22. UBR/22/0389/DWEIN (9 dwellings) IN accepted 3.5.22.
Little Dunmow: The Moors | UTT/18/2600/FUL | 2019-04-12 | 16 | 12 | The Moors, Moors Lane Little Dunmow | -12 | 16 | [19 empty] | Built | 0 | PDL
Manuden: Land north of Stewarts Way | UTT/19/0022/OP | 2021-01-11 | 22 |  | Land To The North Of, Stewarts Way, Manuden |  |  |  | 2025/26 Yr4: 11; 2026/27 Yr5: 11 |  |  |  | 3 | 22 | G |  |  | July 2022 site visit: No works yet undertaken. Aug 22: Agent advised RM app currently being prepared. Envisages an on-site start of late '23/early '24, first occupation in '25, and completion mid-'26.
Newport : Land at Bury Water Lane (Retirement village for 40 bed care home facility and 81 extra care units plus associated communal facilities | UTT/16/0459/OP UTT/17/1561/DFO | 01/11/2016 10 Nov 2017 | 81 |  | Land At Bury Water Lane Bury Water Lane, Newport | 74 | [20 empty] | Built | 0 | G | UTT/13/1817/OP Expires 30 Oct 2016
Newport: Land at Holmwood, Whiteditch Lane | UTT/15/0879/OP UTT/19/1064/DFO | 2020-01-23 | 12 |  | Land At Holmwood Whiteditch Lane Newport CB11 3UD |  |  |  | 2023/24 Yr2: 12 |  |  |  | 2 | 12 | G |  | Agent confirmed details correct (4-Apr-19) | 23.8.22: DoCs and S73 approved 4.3.21 - 4.8.22. Unclear whether works had commenced during July 2022 site visit - agent emailed 12.8.22 to query this.
Newport: Bricketts, London Road | UTT/16/1290/OP UTT/19/2900/DFO | 2016-11-25 | 11 | 1 | Bricketts London Road Newport CB11 3PP |  |  | -1 | 2022/23 Yr1: 11 |  |  |  | 1 | 11 | G |  | Applicant 17.11.20: existing building not yet been demolished. Hope to be on site Feb 2021 and off by Jan 2022 with sales completing soon after that | July 2022 site visit: Works underway. Three dwellings part-built. Existing demolished.
Newport: Land west of London Road | UTT/15/1869/FUL UTT/20/2632/FUL | 2017-10-27 | 89 |  | Land West Of London Road; Newport, Essex |  |  |  | 2023/24 Yr2: 44; 2024/25 Yr3: 45 |  |  |  | 2 | 89 | G |  | UTT/20/2632/FUL Proposal for construction of 89 new dwellings pending decision | UTT/20/2632/FUL approved 24.5.22 (89 dwellings). DoCs approved 4.8.22 - 19.4.22. S73 pending determination. July 2022 site visit: Machinery on-site.
Newport: Site of Redbank | UTT/18/0742/FUL | 2018-05-14 | 6 |  | Site Of Redbank , Bury Water Lane, Newport, CB11 3TZ | 6 | [20 empty] | Built | 0 | PDL
Newport: The Joyce Frankland Academy | UTT/18/0739/FUL | 2020-03-29 | 24 |  | The Joyce Frankland Academy Cambridge Road Newport CB11 3TR |  |  | 6 | 2022/23 Yr1: 18 |  |  |  | 1 | 18 | PDL |  | Agent 31.10.20: should all be completed by 2022 | 1.6.22: Six dwellings built 21-22. Others built 22-23.
Quendon: Land East Of Foxley House | UTT/19/1301/FUL | 2019-11-18 | 9 |  | Land East Of Foxley House Cambridge Road, Quendon |  | 9 | [19 empty] | Built | 0 | G
Saffron Walden: Land at Ashdon Road Commercial Centre | UTT/13/2423/OP UTT/16/2701/DFO | 26-Nov-14 13-Feb17 | 167 |  | Ashdon Road Commercial Centre (Ridgeons) CB10 2NQ | 39 | [20 empty] | Built | 0 | PDL | AC (S106) 30 April 2014 4yrs+2yrs | 39 dwellings completed in 2019/2020 now complete
Saffron Walden: Commercial Centre Ashdon Road | UTT/17/3413/OP UTT/20/0921/DFO | 2019-10-10 | 55 |  | Commercial Centre Ashdon Road Saffron Walden CB10 2NQ |  |  |  | 2025/26 Yr4: 20; 2026/27 Yr5: 35 |  |  |  | 1 | 55 | PDL |  |  | July 2022: Works commenced but at an early stage. Dwellings scheduled to be built in later phase.
Saffron Walden: Land Behind The Old Cement Works, Thaxted Rd | UTT/16/1444/OP UTT/17/3038/DFO UTT/20/0864/FUL | 15-Nov-016 15 Feb 2018 13 May 2021 | 35 |  | Land Behind The Old Cement Works Thaxted Road Saffron Walden CB10 2UR |  |  |  | 2023/24 Yr2: 35 |  |  |  | 1 | 35 | PDL | UTT/13/1937/OP Expires 11 Oct 2016 |  | July 2022 site visit: Fencing erected. DoCs pending determination/approved. UBR/22/0511/DWE (35 dwellings) rejected 9.8.22.
Saffron Walden:Land south of Radwinter Road (excludes C2: 12 extra care bungalows; 30 extra care apartments and excludes 60 bed care home) | UTT/13/3467/OP UTT/16/1856/DFO | 26-May-15 13 Jan 2017 | 200 |  | Land south of Radwinter Road (CB10 2JP) | 37 | 33 | 24 | 2022/23 Yr1: 25 |  |  |  | 1 | 25 | G | AC (S106) 30 April 2014 2yrs+1yrs | 60 bed care home not included - UTT/17/3426/OP refused - appeal lodged | Built figures as per Building Control application.
Saffron Walden: Land North Of Shire Hill Farm | UTT/17/2832/OP | 2020-07-14 | 100 |  | Land North Of Shire Hill Farm, Shire Hill, Saffron Walden |  |  |  | 2023/24 Yr2: 33; 2024/25 Yr3: 33; 2025/26 Yr4: 34 |  |  |  | 3 | 100 | G |  | UTT/21/3565/DFO pending consideration | 13.5.22: UTT/21/1920/NMA approved 9.7.21. UTT/21/3565/DFO received 30.11.21 and pending. DoCs approved/pending. UBR/22/0181/DWEIN (100 dwellings) received 23.2.22.
Saffron Walden: Land off Little Walden Road | UTT/16/2210/OP UTT/18/2959/DFO | 2020-05-12 | 85 |  | Land Off Little Walden Road Saffron Walden |  |  | 1 | 2022/23 Yr1: 42; 2023/24 Yr2: 42 |  |  |  | 1 | 84 | G |  | Agent Nov 2021: Plots 1 – 3 are complete. Plots 4 – 21, 47 - 53 are currently under build. Site is due to be completed October 2023. | UBR/20/0620/DWE (85 dwellings): one built 21-22. Others built 22-23.
Saffron Walden: Police Station, East Street | UTT/17/3662/FUL | 2018-02-15 | 7 |  | Police Station East Street Saffron Walden CB10 1LR | 7 | [20 empty] | Built | 0 | PDL
Saffron Walden: Former Walden Dairy | UTT/18/3399/FUL | 2019-11-08 | 7 |  | Former Walden Dairy 135 Thaxted Road Saffron Walden, CB11 3BJ |  |  |  | 2022/23 Yr1: 7 |  |  |  | 2 | 7 | PDL |  |  | July 2022 site visit: Fencing in-situ and office containers on-site. NMAT approved 25.10.21.
Saffron Walden: Land at Thaxted Road | UTT/18/2820/FUL | 2019-10-23 | 14 |  | Land At Thaxted Road Saffron Walden |  |  |  | 2022/23 Yr1: 14 |  |  |  | 1 | 14 | PDL |  |  | UBR/20/0099/DWE (14 dwellings) Work Started on all plots 6.5.21 - 21.9.21. None completed as of 14.4.22.
Saffron Walden: Land East of Thaxted Road | UTT/18/0824/OP UTT/19/2355/DFO | 2019-04-12 | 150 |  | Land East Of Thaxted Road Saffron Walden |  |  |  | 2022/23 Yr1: 28; 2023/24 Yr2: 55; 2024/25 Yr3: 60; 2025/26 Yr4: 7 |  |  |  | 1 | 150 | G |  | Agent 17.11.20 Development commenced. Completions estimated to be 28 units to Jan 2023, 55 units in 2023, 60 units in 2024 and the remainder in 2025. | July 2022 site visit: Works underway and advanced. First homes to be marketed week commencing 10.12.22 (as advised by site manager).
Stansted Mountfitchet: Land at Walpole Farm | UTT/13/1618/OP UTT/15/2746/DFO | 1 april 2014 15 Feb 2016 | 147 |  | Land At Walpole Farm Cambridge Road Stansted CM24 8TA | 16 | [20 empty] | Built | 0 | G | UTT/13/1618/OP app S106 25/9/13 Decision issued 1 April 2014 (2yrs + 1yr)
Stansted Mountfitchet: Land north of Water Lane | UTT/16/2865/OP UTT/19/2388/DFO | 09/02/2017 19 Jun 2020 | 9 |  | Land North Of Water Lane Stansted |  |  |  | 2022/23 Yr1: 9 |  |  |  | 1 | 9 | G |  |  | July 2022 site visit: ground works underway.
Stansted Mountfitchet: The Three Colts, Cambridge Road | UTT/17/1304/FUL | 2017-07-03 | 6 |  | The Three Colts 86 Cambridge Road Stansted, CM24 8DB | 6 | [20 empty] | Built | 0 | PDL
Stansted Mountfitchet: Land To The West Of High Lane | UTT/18/1993/FUL | 2019-05-30 | 35 |  | Land To The West Of High Lane Stansted |  | 35 | [19 empty] | Built | 0 | G
Stansted Mountfitchet: Land Adjacent The Stables | UTT/19/1986/FUL UTT/20/1817/FUL | 2020-11-30 | 6 |  | Land Adjacent The Stables High Lane Stansted CM24 8LQ |  | 6 | [19 empty] | Built | 0 | G
Stebbing: land to east of Parkside and rear of Garden Fields | UTT/14/1069/OP UTT/17/3538/DFO | 01-Feb-15 (16-Apr-18) | 30 |  | Ld Nth of Stebbing primary school R/o Gdn Fields & Parkside, Stebbing (CM6 3RA) | 16 | [20 empty] | Built | 0 | G
Stebbing: Land east of Warehouse Villas | UTT/19/0476/OP | 2022-02-23 | 17 |  | Land east of Warehouse Villas, Stebbing Road, Stebbing, Essex |  |  |  | 2023/24 Yr2: 7; 2024/25 Yr3: 10 |  |  |  | 3 | 17 | G |  |  | 23.8.22: UTT/22/0676/DFO approved 18.7.22. UBR/22/0497/DWE (7 dwellings) rejected 28.7.22; and UBR/22/0539/DWEIN (10 dwellings) IN accepted 10.6.22. Aug 22: Agent advised that 22/0676 relates to 7 affordable units and that the remaining 10 are subject to a second RM. Advised the approved 7 are at the stage of detailed design.
Stebbing: Sabre House, Dunmow Road | UTT/17/2480/OP | 2017-11-28 | 9 |  | Sabre House, Dunmow Road, Stebbing, CM6 3LF |  |  |  | 2025/26 Yr4: 9 |  |  |  | 3 | 9 | PDL |  | UTT/21/0333/OP refused. Appeal in progress.
Takeley: Land south of The Street | UTT/18/2049/FUL | 2020-09-04 | 8 |  | Land To The South Of The Street, Takeley, CM22 6LY |  |  |  | 2022/23 Yr1: 8 |  |  |  | 1 | 8 | G |  |  | July 2022 site visit: Works underway. All dwellings nearing completion.
Takeley: Land between 1 Coppice Close and Hillcroft, south of B1256 Takeley Street | UTT/17/1852/FUL | 2018-05-18 | 20 |  | Land Adj To Coppice Close Dunmow Road, Takeley |  |  |  | 2022/23 Yr1: 20 |  |  |  | 1 | 20 | G |  |  | July 2022 site visit: Works underway. All dwellings part-built.
Takeley: Land North Of Dunmow Road | UTT/18/2917/FUL | 2019-01-22 | 8 |  | Land North Of Dunmow Road East Of Church Lane Dunmow Road, Takeley | 8 | [20 empty] | Built | 0 | G
Takeley: Land To The South Of School Lane | UTT/19/1583/FUL | 2019-10-24 | 8 |  | Land To The South Of School Lane, Takeley |  | 8 | [19 empty] | Built | 0 | G
Takeley: Land West Of Parsonage Road | UTT/19/0393/OP | 2020-01-31 | 119 |  | Land West Of Parsonage Road, Takeley |  |  |  | 2024/25 Yr3: 29; 2025/26 Yr4: 45; 2026/27 Yr5: 45 |  |  |  | 3 | 119 | G |  | Agent Nov 2021: Plan to submit RM 2022, to start 2023. Full site completion Dec 2025 | 15.5.22: NMATs and DoC approved 21.4.21 to 7.3.22. UTT/22/0152/DFO (reduced to 110 dwellings) approved 4.5.22. UBR/22/0388/DWEIN (110 dwellings) IN accepted 4.5.22. Figures to be amended for 22-23.
Takeley: Remarc | UTT/20/0386/FUL | 2020-02-07 | 8 |  | Remarc, Dunmow Road Takeley CM22 6SP |  |  |  | 2023/24 Yr2: 8 |  |  |  | 2 | 8 | PDL |  |  | 16.5.22: UBR/22/0226/DOM (8 flats) received 13.4.22.
Thaxted: Former Molecular Products Ltd site, Mill End | UTT/16/0171/FUL UTT/17/1444/FUL | 2016-09-29 | 29 |  | Molecular Products Ltd. Mill End Thaxted CM6 2LT | 7 | 9 | [19 empty] | Built | 0 | PDL |  | 9 completed 2020/21. Previous years checked and 2018/2019 adjusted to 6
Thaxted: Former Molecular Products Ltd site | UTT/19/0671/FUL | 2019-10-29 | 8 | 1 | Molecular Products Ltd. Mill End, Thaxted, CM6 2LT |  | 8 | [19 empty] | Built | 0 | PDL |  | Amendment to UTT/17/1444/FUL change from 4 dwellings (1x2bed, 1x3bed and 2x4bed) into 8 apartments (1x1 bed and 7 x 2 bed)
Thaxted: Land at Little Maypole | UTT/16/3255/FUL | 2018-04-05 | 9 |  | Land At Little Maypole Thaxted | 9 | [20 empty] | Built | 0 | G
Thaxted: Warners Field, Copthall Lane | (UTT/17/1896/FUL) UTT/20/2624/FUL | 2018-04-19 | 7 |  | J F Knight Roadworks Ltd (Warners Field), Copthall Lane, Thaxted, CM6 2LG |  |  |  | 2022/23 Yr1: 7 |  |  |  | 1 | 7 | PDL |  |  | DoCs and NMATs approved 15.10.21 to 9.5.22. July 2022 site visit: Works underway.
Thaxted: Land East of Claypit Villas | UTT/17/3571/FUL | 2018-12-10 | 9 |  | Land East Of Claypit Villas Bardfield Road Thaxted |  |  |  | 2022/23 Yr1: 9 |  |  |  | 1 | 9 | G |  |  | UBR/21/0995/DWE (9 dwellings) Work Started 18.11.21.
Thaxted: Cutlers Green Farm | UTT/18/2055/FUL | 2019-03-14 | 6 |  | Cutlers Green Farm Cutlers Green, Cutlers Green Lane, Thaxted |  |  |  | 2022/23 Yr1: 6 |  |  |  | 1 | 6 | PDL |  | Looking for a developer to advance the project. Unlikely that much action will happen before 2022 | July 2022 site visit: Works underway. One dwelling (plot 1) superseded and built.
Thaxted: Claypits Farm, Bardfield Road | UTT/18/0750/OP UTT/20/0614/OP | 14/03/2019 28 Oct 2021 | 14 |  | Land At Claypits Farm Bardfield Road Thaxted, CM6 3PU |  |  |  | 2024/25 Yr3: 14 |  |  |  | 3 | 14 | PDL |  | UTT/20/0614/OP approved on appeal 28/10/2021 | 6.6.22: UTT/22/1020/FUL pending determination.
Wendens Ambo: Mill House, Royston Road | UTT/17/2270/PAP3O UTT/18/3455/PAP3O UTT/19/1631/PAO3 | 2017-09-17 | 15 |  | Mill House Royston Road Wendens Ambo, CB11 4JX |  | 15 | [19 empty] | Built | 0 | PDL
White Roding: Westons Yard, Chelmsford Road | UTT/17/0952/OP UTT/18/2523/FUL | 2017-06-16 | 7 |  | Westons Yard, Chelmsford Road, White Roding, CM6 1RF | 3 | 4 | [19 empty] | Built | 0 | PDL
TOTAL COMPLETIONS | [5 empty] | 497 | 362 | 208 | [19 empty] | 1067
TOTAL EXISTING COMMITMENTS | [8 empty] | 465 | 603 | 708 | 579 | 477 | 281 | 255 | 220 | 195 | 125 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3968
Planning permission small sites (647 net permissions - assume 63% delivered - spread over three years) | [8 empty] | 2022/23 Yr1: 136; 2023/24 Yr2: 136; 2024/25 Yr3: 136
WINDFALL ALLOWANCE | [11 empty] | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 |  | 1710
Commitments and windfall total | [8 empty] | 601 | 739 | 844 | 693 | 591 | 395 | 369 | 334 | 309 | 239 | 174 | 114 | 114 | 114 | 114 | 114 | 114 | 114 |  | 6086
Communal Establishments
Newport: Land at Bury Water Nursuries | UTT/17/1561/DFO | 2017-11-10 | 40 |  | Land At Bury Water Nurseries Whiteditch Lane Newport | 40 | [20 empty] | Built | 0 | G
Saffron Walden: Land south of Radwinter Road | UTT/17/3426/OP UTT/21/2465/DFO | 26/05/2015 1 Oct 2021 | 72 |  | Land South Of Radwinter Road Radwinter Road Saffron Walden |  |  |  | 2023/24 Yr2: 72 |  |  |  | 2 | 72 | PDL |  | UTT/21/2465/DFO increases C2 from 60 to 72 beds. Permitted Oct 2021 33 x 1 bed apartments, 23 x 2 bed apartments, 7 x 1 bed bungalows, 9 x 2 bed bungalows. Intial Building control Oct 2021 | 9.6.22: DoCs approved 24.3.22 - 31.5.22. Others pending determination. UBR/21/1022/DWEIN (72 units) Initial Notice accepted 26.10.21.
Takeley: Land east of Parsonage Road | UTT/19/0394/OP | 2020-01-31 | 66 |  | Land East Of, Parsonage Road, Takeley |  |  |  | 2025/26 Yr4: 66 |  |  |  | 3 | 66 | G |  |  | July 2022 site visit: No works yet undertaken. Aug 22: Agent advised, as per developer, that a RM app is due in early '23 with completion expected within 18-24 months of the approval of all necessary details.
Great Dunmow: 77 High Steet | UTT/19/1437/FUL | 2021-03-16 | 29 |  | 77 High Street Great Dunmow CM6 1AE |  |  |  | 2022/23 Yr1: 29 |  |  |  | 1 | 29 |  |  | Agent: expected completion March 2023 | UBR/18/0590/DWEIN (29 units) Initial Notice accepted 4.7.18. July 2022 site visit: Works ongoing.
TOTAL COMMUNAL ESTABLISHMENTS | [5 empty] | 40 | 0 | 0 | 29 | 72 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 207
TOTAL COMMUNAL ESTABLISHMENTS ADJUSTED | [5 empty] | 22 | 0 | 0 | 16 | 40 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 115
TOTAL DELIVERY | [5 empty] | 519 | 362 | 208 | 617 | 779 | 844 | 729 | 591 | 395 | 369 | 334 | 309 | 239 | 174 | 114 | 114 | 114 | 114 | 114 | 114 | 114 |  | 7267
KEY FOR STATUS (column AQ)
Under construction |  | 1
with planning permission (full or reserved matters covering whole site) |  | 2
with outline permission with part(s) covered by reserved matters |  | 3
with outline only |  | 4
where full, outline or reserved matters at post committee resolution subject to S106 negotiations |  | 5
with application submitted |  | 6
with pre-application discussions occurring |  | 7
allocation only |  | 8
draft allocation – zero currently from this source |  | 9
COLOUR KEY
Permissions absent from previous 5YHLS mastersheets